# PROJECT COST MANAGEMENT

Project Title: University Financial Management System (FMS)

## 1. Cost Management Plan

### 1.1 Purpose

The Cost Management Plan defines how project costs for the University Financial Management System will be planned, estimated, budgeted, and controlled to ensure the project is delivered within the approved financial limits.

### 1.2 Cost Estimation Approach

Project cost estimates are developed using:

- Bottom-up estimation based on the Work Breakdown Structure

- Expert judgment from technical and financial stakeholders

- Analogous estimation using previous university IT systems

All costs are estimated in Egyptian Pounds and prepared prior to project execution.

### 1.3 Cost Assumptions and Constraints

Assumptions

- Internal university infrastructure will be used where possible

- Existing systems will be reused to minimize cost

Constraints

- Budget must comply with university financial regulations

- Funding approvals follow internal governance procedures

### 1.4 Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager | Prepares cost plan and manages budget |
| Finance Representative | Reviews and validates estimates |
| Development Lead | Provides development cost inputs |
| QA Lead | Supports testing cost estimation |
| Project Sponsor | Approves cost baseline |

## 2. Cost Baseline

### 2.1 Cost Estimates by WBS

| WBS Component | Estimated Cost (EGP) |
| --- | --- |
| Project Initiation | 30,000 |
| System Design | 40,000 |
| Student Payment Module | 60,000 |
| Budget and Expenditure Module | 70,000 |
| Reporting and Analytics | 40,000 |
| Audit and Access Control | 35,000 |
| System Integration | 30,000 |
| Testing and Quality Assurance | 50,000 |
| Deployment | 25,000 |
| Training and Documentation | 20,000 |
| Project Closure | 10,000 |
| Total Direct Cost | 410,000 |

### 2.2 Overhead Costs

| Overhead Item | Cost (EGP) |
| --- | --- |
| Project Management | 40,000 |
| Tools and Software Licenses | 10,000 |
| Hosting and Infrastructure | 10,000 |
| Total Overhead Cost | 60,000 |

### 2.3 Total Estimated Project Cost

- Direct project costs: 410,000 EGP

- Overhead costs: 60,000 EGP

Total Estimated Cost = 470,000 EGP

### 2.4 Contingency and Management Reserves

Contingency Reserve

- Allocated to cover identified project risks

- Set at fifteen percent of total estimated cost

Contingency Reserve Amount = 70,500 EGP

Management Reserve

- Allocated for unforeseen risks

- Controlled by the project sponsor

Management Reserve Amount = 20,000 EGP

### 2.5 Cost Baseline

| Component | Amount (EGP) |
| --- | --- |
| Total Estimated Cost | 470,000 |
| Contingency Reserve | 70,500 |
| Cost Baseline | 540,500 EGP |

## 3. Cost Controls

### 3.1 Purpose of Cost Controls

Cost controls define the processes and rules used to ensure that project spending remains aligned with the approved cost baseline. The objective is to detect cost deviations early and enable corrective action.

### 3.2 Cost Monitoring Methods

The project will apply the following cost control mechanisms:

- Regular comparison of planned budget against actual expenditures

- Monitoring of labor usage and resource allocation

- Review of supplier invoices and expenses

- Phase-end financial reviews

### 3.3 Variance Thresholds

- Cost variance up to ten percent is acceptable and monitored

- Variance above ten percent requires investigation

- Variance above fifteen percent requires corrective action and sponsor approval

### 3.4 Change Control and Cost Impact

Any change that affects project cost must follow the formal change control process. Changes impacting the cost baseline require approval from the project sponsor and finance department before implementation.

### 3.5 Reporting and Documentation

- Cost status is reviewed during key project milestones

- Approved changes are reflected in updated budget documents

- Cost records are maintained for audit and reporting purposes