# FMS Project Activity List

a

Contents

FMS Project Activity List	2

Increment 1	2

Requirement Analysis	2

System Design	2

Project Setup	3

Increment 2	3

Requirements Analysis	3

System Design	3

Implementation	3

Testing	4

Increment 3	4

Requirement Analysis	4

Design	4

Implementation	4

Testing	5

Increment 4	5

Requirements/Design	5

Implementation	5

Testing	6

Increment 5	6

Design & Implementation	6

Testing	6

Increment 6	7

Integration	7

UAT	7

Deployment & Training	7

# Increment 1

## Requirement Analysis

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 1 | Identify key stakeholders | Identify finance, IT, admin, PMO stakeholders | Stakeholder list | - |
| 2 | Conduct requirement-gathering sessions | Workshops with Finance Department | Requirement notes | 1 |
| 3 | Define project & increment objectives | Document high-level goals | Project objectives | 2 |
| 4 | Validate and approve documented requirements | Finalize SRS scope | Approved requirements | 3 |

## System Design

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 5 | Draft architecture diagram | Initial system architecture | Architecture diagram | 4 |
| 6 | Design preliminary ERD | Database structure | ERD v1 | 5 |
| 7 | Draft UI wireframes | Basic UI design | Wireframe set | 6 |

## Project Setup

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 8 | Establish development environment | Install frameworks, tools | Working environment | 7 |
| 9 | Configure GitHub repository | Create repo, permissions | GitHub repo | 8 |
| 10 | Define WBS and baseline | Define WBS + schedule | WBS + Baseline | 9 |

# Increment 2

## Requirements Analysis

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 11 | Collect payment workflow rules | Map payment logic | Workflow map | 10 |
| 12 | Update SRS with payment features | Add fields, validations | Updated SRS | 11 |

## System Design

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 13 | Update ERD (Payment) | Add payment tables | ERD v2 | 12 |
| 14 | Design UI mockups | UI for payment portal | Mockup set | 13 |

## Implementation

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 15 | Backend payment API | Create controllers, validation | Payment API | 14 |
| 16 | Frontend payment UI | Develop payment interface | Payment UI | 14 |
| 17 | Integrate payment gateway | Simulated payment processing | Gateway integration | 15,16 |
| 18 | Generate & test receipts | PDF/Excel generation | Receipt output | 17 |

## Testing

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 19 | Unit testing | Test logic | Unit test report | 15,16 |
| 20 | Integration testing | Auth ↔ payment | Integration report | 19,17 |

# Increment 3

## Requirement Analysis

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 21 | Identify budgeting needs | Budget needs collection | Budget requirements | 20 |

## Design

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 22 | Update ERD & DFD | ERD v3 + DFD | ERD/DFD | 21 |
| 23 | Design budget UI | Mockups for budget | Budget UI | 22 |

## Implementation

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 24 | Develop budget APIs | Budget endpoints | Budget API | 23 |
| 25 | Integrate ledger data | Budget vs actual | Ledger integration | 24 |
| 26 | Update database schema | Add new tables | DB schema | 25 |

## Testing

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 27 | Module-level testing | Budget module tests | Test report | 26 |
| 28 | Regression testing | Compatibility check | Regression report | 27 |

# Increment 4

## Requirements/Design

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 29 | Gather reporting requirements | Identify KPIs | Reporting needs | 28 |
| 30 | Design ETL logic | ETL workflow | ETL diagrams | 29 |
| 31 | Dashboard mockups | Dashboard UI | UI mockups | 30 |

## Implementation

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 32 | Backend report generation | Generate PDF/Excel | Reporting engine | 31 |
| 33 | Frontend dashboards | Charts, KPIs | Dashboards | 31 |
| 34 | Integrate reporting module | Integration with Budget/Ledger | Integrated module | 32,33 |

## Testing

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 35 | Reporting tests | Test reporting logic | Test results | 34 |
| 36 | UAT (Reporting) | Review with users | UAT sign-off | 35 |

# Increment 5

## Design & Implementation

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 37 | Define RBAC requirements | Role mapping | RBAC plan | 36 |
| 38 | Implement roles & permissions | RBAC build | Role module | 37 |
| 39 | Implement audit logs | Log all key transactions | Audit logs | 38 |
| 40 | Security optimization | Hardening | Optimized module | 39 |

## Testing

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 41 | Penetration testing | Security tests | Pen-test report | 40 |
| 42 | RBAC validation | Test permissions | RBAC test report | 41 |

# Increment 6

## Integration

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 43 | Integrate all modules | Combine Payment/Budget/Reporting/Audit | Integrated FMS | 42 |
| 44 | System testing | End-to-end testing | System test report | 43 |

## UAT

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 45 | Conduct UAT sessions | Finance dept testing | UAT feedback | 44 |
| 46 | Resolve UAT issues | Fixes + retesting | Retest approval | 45 |

## Deployment & Training

| ID | Activity Name | Description | Deliverable | Predecessor |
| --- | --- | --- | --- | --- |
| 47 | Prepare deployment environment | Setup servers | Deployment environment | 46 |
| 48 | Deploy FMS system | Deploy on servers | Live system | 47 |
| 49 | Training sessions | Train finance staff | Training completion | 48 |