RESOURCE MANAGEMENT PLAN

1. Introduction

This Project Resource Management Plan defines the processes, structures, and methodologies used to identify, classify, allocate, and manage resources throughout the Financial Management System (FMS) project. The purpose of this plan is to ensure that the right resources are available at the right time and fully aligned with project objectives. ProjectLibre is used as the primary tool for resource definition, assignment, tracking, and utilization analysis.

2. Resource Management Objectives

The main objectives of resource management in this project are:

- Ensure proper identification and classification of all project resources.

- Assign resources at the activity level, not summary tasks, following PMI standards.

- Allocate work based on the correct unit percentage (%) for each resource.

- Maintain efficient workload distribution and avoid over-allocation.

- Ensure each project increment receives the correct functional expertise.

3. Resource Breakdown Structure (RBS)

The project resources are organized into a four-level hierarchical RBS:

Level 1: Management Resources

- University Administration

- Finance Department

Level 2: Technical / Development Resources

- Project Technical Management

- Backend Development Team

- Frontend Development Team

- Database Team

- Cloud & Infrastructure Team

- Quality Assurance & Testing Team

- Security Team

Level 3: Operations / Support Resources

- Student Affairs Support Team

- Faculties Administration Team

Level 4: External Resources

- External Audit & Compliance

This RBS was fully implemented into ProjectLibre and used to populate the Resource Sheet.

4. Resource Identification and Categorization

Each resource was assigned one of four main categories:

- Management: Strategic oversight, approvals, stakeholder decision-making.

- Technical: Architecture, design, development, infrastructure, security, testing.

- Operations: UAT participation, process validation, student/departmental data.

- External: Audit, compliance, vendor support.

This classification allowed consistent grouping inside ProjectLibre using the Group column.

5. Resource Assignment Strategy

Resources were assigned only to detailed activity tasks, never to summary tasks, in compliance with professional project management standards.

Assignment Principles:

- Activities involving business rules → Finance Department (50%) + Technical PM (50%)

- System design tasks → Technical teams (Frontend, Backend, Database)

- Development tasks → Backend/Frontend at 100%

- Testing tasks → QA Team (100%)

- Security tasks → Security Team (100%)

- UAT → Finance + University Admin (50% / 50%)

- Deployment → Infrastructure (100%) + Backend (50%)

- Architecture and planning → Technical PM (100%)

6. Resource Allocation Method (Unit Percentages)

Activities involving:

- One resource → 100%

- Two resources → 50% / 50%

- Three resources → 33% each

This method ensures proper effort distribution and prevents ProjectLibre from marking tasks as overloaded.

7. Resource Monitoring & Control

Resource usage is monitored through:

- Resource Usage View

- Overallocation indicators (red flags)

- Critical Path recalculations

- Sprint/increment reviews

- Weekly resource performance tracking

Corrective actions include reassignment, load balancing, or adjusting task duration.

8. Tools Used

- ProjectLibre Resource Sheet for resource definition

- ProjectLibre Gantt Chart for activity-level assignments

- ProjectLibre RBS View for hierarchy organization

- Stakeholder Register

- System Requirements Specification (SRS)