Risk Register – University Financial Management System (FMS)

| ID | Risk Description | Category | Owner | Prob (Score) | Impact (Score) | Risk Score | Priority | Response Strategy | Mitigation Actions | Trigger | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Delay in requirements approval from Finance Dept | Stakeholder | PM | Medium (2) | High (3) | 6 | High | Mitigate | Early workshops, fixed approval deadlines | Missed approval date | Open |
| R2 | Underestimation of system integration effort with legacy systems | Technical | Dev Lead | Medium (2) | High (3) | 6 | High | Mitigate | Early integration prototyping, buffer time | Integration defects increase | Open |
| R3 | Additional testing cycles increase project cost | Quality / Cost | QA Lead | Medium (2) | Medium (2) | 4 | Medium | Mitigate | Improve test planning, automation | Rising defect backlog | Open |
| R4 | Cost overrun due to inefficient resource utilization (CPI < 0.9) | Financial | Finance Rep | Medium (2) | High (3) | 6 | High | Mitigate | Resource optimization, weekly CPI review | CPI < 0.9 | Open |
| R5 | Schedule delay due to dependency issues between modules | Schedule | PM | Medium (2) | High (3) | 6 | High | Mitigate | Dependency review, critical path monitoring | Missed milestone | Open |
| R6 | Scope creep after baseline approval | Scope | PM | Medium (2) | High (3) | 6 | High | Avoid | Strict change control, sponsor approval | New unapproved requests | Open |
| R7 | Limited IT resource availability during peak academic periods | Resource | IT Manager | Medium (2) | Medium (2) | 4 | Medium | Mitigate | Adjust schedule, backup resources | Reduced staff availability | Open |
| R8 | Security vulnerabilities discovered late in development | Security | Security Lead | Low (1) | High (3) | 3 | Medium | Mitigate | Early security testing, code reviews | Security scan alerts | Open |
| R9 | Audit non-compliance findings during external review | Compliance | Audit Rep | Low (1) | High (3) | 3 | Medium | Mitigate | Pre-audit reviews, compliance checks | Audit warnings | Open |
| R10 | User resistance during UAT | Stakeholder | QA Lead | Medium (2) | Medium (2) | 4 | Medium | Mitigate | Training, demos, early involvement | Negative UAT feedback | Open |
| R11 | Data migration errors during deployment | Technical | Dev Lead | Low (1) | High (3) | 3 | Medium | Mitigate | Data validation, test migrations | Migration failures | Open |
| R12 | Cash flow deviation from planned S-curve | Financial | Finance Rep | Low (1) | Medium (2) | 2 | Low | Accept | Monitor cash flow, periodic reviews | S-curve variance | Open |

Note: Prob/Impact scores are on a 1–3 scale; Risk Score = Prob x Impact.