# PROJECT COST MANAGEMENT

Project Title: University Financial Management System (FMS)

## 1. Cost Management Plan

### 1.1 Purpose

The Cost Management Plan defines how project costs for the University Financial Management System will be planned, estimated, budgeted, monitored, and controlled to ensure delivery within the approved financial limits.

### 1.2 Cost Estimation Approach

Project costs are estimated using:

- Bottom-up estimation based on the Work Breakdown Structure

- Expert judgment from IT and finance stakeholders

- Analogous estimation using previous university systems

All costs are estimated in Egyptian Pounds (EGP) and rounded to the nearest hundred.

### 1.3 Assumptions and Constraints

Assumptions

- Internal university infrastructure is utilized

- Existing systems are reused where possible

- No mobile or payroll systems are included

Constraints

- Budget must comply with university financial policies

- Funding approval follows internal governance procedures

### 1.4 Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager | Prepare and manage project cost plan |
| Finance Representative | Validate cost estimates |
| Development Lead | Estimate development effort |
| QA Lead | Estimate testing effort |
| Project Sponsor | Approve cost baseline |

## 2. Cost Baseline

### 2.1 Cost Estimates by WBS

| WBS Component | Estimated Cost (EGP) |
| --- | --- |
| Project Initiation | 30,000 |
| System Design | 40,000 |
| Student Payment Module | 60,000 |
| Budget and Expenditure Module | 70,000 |
| Reporting and Analytics | 40,000 |
| Audit and Access Control | 35,000 |
| System Integration | 30,000 |
| Testing and Quality Assurance | 50,000 |
| Deployment | 25,000 |
| Training and Documentation | 20,000 |
| Project Closure | 10,000 |
| Total Direct Cost | 410,000 |

### 2.2 Overhead Costs

| Overhead Item | Cost (EGP) |
| --- | --- |
| Project Management | 40,000 |
| Tools and Licenses | 10,000 |
| Hosting and Infrastructure | 10,000 |
| Total Overheads | 60,000 |

### 2.3 Total Estimated Project Cost

Total estimated project cost before reserves:

Direct costs: 410,000 EGP
Overheads: 60,000 EGP

Total Estimated Cost = 470,000 EGP

### 2.4 Reserves

Contingency Reserve
Allocated to cover identified risks such as integration issues and additional testing.
Set at fifteen percent of estimated cost.

Contingency Reserve = 70,500 EGP

Management Reserve
Allocated for unforeseen risks and controlled by the sponsor.

Management Reserve = 20,000 EGP

### 2.5 Cost Baseline

| Component | Amount (EGP) |
| --- | --- |
| Total Estimated Cost | 470,000 |
| Contingency Reserve | 70,500 |
| Cost Baseline | 540,500 EGP |

## 3. Cost Controls

### 3.1 Purpose of Cost Controls

Cost controls ensure that project expenditures remain aligned with the approved cost baseline and enable early identification of cost deviations.

### 3.2 Earned Value Management (EVM)

Earned Value Management is used as the primary technique for cost control. The following metrics are applied:

- Planned Value (PV)

- Earned Value (EV)

- Actual Cost (AC)

### 3.3 EVM Assumptions

For planning and academic evaluation, the following assumptions are made:

- Development phase budget: 250,000 EGP

- Development duration: 10 weeks

- Planned value per week: 25,000 EGP

### 3.4 Status Review at Week 6 (Assumed Scenario)

Planned Value (PV)
PV equals planned weekly cost multiplied by time elapsed.

PV = 25,000 × 6 = 150,000 EGP

Earned Value (EV)
Earned Value is calculated based on the percentage of work completed.

| Module | Budget (EGP) | Completion % | EV |
| --- | --- | --- | --- |
| Student Payment Module | 60,000 | 100% | 60,000 |
| Budget Module | 70,000 | 50% | 35,000 |
| Reporting Module | 40,000 | 40% | 16,000 |
| Audit Module | 35,000 | 20% | 7,000 |
| Integration | 30,000 | 0% | 0 |
| Total EV |  |  | 118,000 |

Actual Cost (AC)
Actual spending reported at week six:

AC = 130,000 EGP

### 3.5 EVM Calculations

Cost Variance (CV)
CV = EV − AC
CV = 118,000 − 130,000 = −12,000 EGP

Project is slightly over budget.

Schedule Variance (SV)
SV = EV − PV
SV = 118,000 − 150,000 = −32,000 EGP

Project is behind schedule.

Cost Performance Index (CPI)
CPI = EV ÷ AC
CPI = 0.91

Schedule Performance Index (SPI)
SPI = EV ÷ PV
SPI = 0.79

### 3.6 Forecasting

Estimate at Completion (EAC)
EAC = Budget at Completion ÷ CPI
EAC = 250,000 ÷ 0.91 = 274,700 EGP

Estimate to Complete (ETC)
ETC = EAC − AC
ETC = 144,700 EGP

### 3.7 Interpretation and Corrective Actions

- CPI less than one indicates inefficient cost utilization

- SPI less than one indicates schedule delay

- Overrun is within contingency reserve

- Corrective actions include workload reallocation and tighter task prioritization