Project Risk Management Plan

Project Title: University Financial Management System (FMS)

1. Purpose

The purpose of this Risk Management Plan is to define the processes, tools, roles, and responsibilities for identifying, analyzing, responding to, monitoring, and controlling risks throughout the Financial Management System (FMS) project.

Effective risk management ensures that potential threats to scope, schedule, cost, quality, security, and regulatory compliance are proactively addressed, minimizing negative impacts and increasing the likelihood of delivering the project within the approved baselines.

2. Risk Management Objectives

The objectives of risk management for this project are to:

- Identify potential risks early across all project phases and increments

- Analyze risks using probability–impact scoring

- Prioritize risks based on quantified risk scores

- Define proactive mitigation and contingency responses

- Monitor cost and schedule risks using Earned Value indicators (CPI, SPI)

- Ensure compliance with university financial, audit, and security regulations

- Protect the approved cost and schedule baselines, including contingency and management reserves

3. Risk Management Methodology

Risk management activities follow PMBOK® best practices and are performed continuously throughout the project lifecycle.

3.1 Risk Identification

Risks are identified during:

- Planning workshops

- Increment reviews

- Milestone checkpoints

Sources include:

- Scope baseline and WBS

- Schedule Management Plan

- Cost baseline and S-curve

- Stakeholder Register

- Lessons learned

3.2 Qualitative Risk Analysis

Each identified risk is assessed using Probability and Impact scales.

Risk Scoring Formula:

Risk Score = Probability × Impact

Where:

- Low = 1

- Medium = 2

- High = 3

Risk scores range from 1 to 9 and are used to prioritize risks.

3.3 Risk Response Planning

For each prioritized risk, an appropriate response strategy is defined:

- Avoid – eliminate the risk by changing the project approach

- Mitigate – reduce probability and/or impact

- Transfer – shift risk to a third party (where applicable)

- Accept – acknowledge the risk and monitor

Each response includes:

- Assigned Risk Owner

- Defined Mitigation Actions

- Identified Risk Triggers

- Assessment of Residual Risk

3.4 Risk Monitoring and Control

Risk monitoring includes:

- Bi-weekly risk reviews

- Increment-end reassessments

- Review of risk triggers

- Monitoring CPI, SPI, and milestone performance

New risks are added to the Risk Register as they are identified, and existing risks are re-evaluated.

4. Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Owns risk process, maintains register, escalates high risks |
| Project Sponsor | Approves contingency & management reserve usage |
| Finance Representative | Reviews cost and cash-flow risks |
| Development Lead | Owns technical and integration risks |
| QA Lead | Owns quality, testing, and UAT risks |
| IT / Security Team | Owns infrastructure and security risks |
| External Auditors | Identify compliance and audit risks |

Each risk in the Risk Register is assigned a Risk Owner responsible for monitoring and response.

Risks for the FMS project are classified into the following categories:

- Technical Risks: Integration issues, system performance, security vulnerabilities.

- Schedule Risks: Increment delays, dependency misalignment, late approvals.

- Cost Risks: Underestimation, inefficient resource usage, CPI < 1.

- Scope Risks: Scope creep, unclear requirements, rework.

- Resource Risks: Skill gaps, overallocation, limited availability.

- Stakeholder Risks: Low engagement, delayed feedback, resistance to change.

- Compliance & Audit Risks: Regulatory non-compliance, audit findings.

- External Risks: Policy changes, infrastructure constraints.

.

6. Probability and Impact Definitions

Probability Scale

| Level | Definition | Score |
| --- | --- | --- |
| Low | < 30% chance | 1 |
| Medium | 30%–60% chance | 2 |
| High | > 60% chance | 3 |

Impact Scale

| Level | Definition | Score |
| --- | --- | --- |
| Low | No baseline change | 1 |
| Medium | Manageable within contingency | 2 |
| High | Requires sponsor approval | 3 |

7. Probability–Impact Matrix

| Probability ↓ / Impact → | Low (1) | Medium (2) | High (3) |
| --- | --- | --- | --- |
| High (3) | 3 (Medium) | 6 (High) | 9 (High) |
| Medium (2) | 2 (Low) | 4 (Medium) | 6 (High) |
| Low (1) | 1 (Low) | 2 (Low) | 3 (Medium) |

8. Risk Thresholds and Escalation

Risk escalation is triggered when:

- Cost variance exceeds 10% of planned value.

- Schedule delay exceeds one week per increment.

- CPI or SPI drops below 0.9.

- Risk impact threatens a major milestone or compliance requirement.

Escalated risks are reviewed by the Project Sponsor and Finance Department.

9. Risk Triggers

Risk triggers are early warning signs indicating that a risk may occur.

Examples:

- Missed milestone dates

- Increasing defect rates

- CPI/SPI trending downward

- Delayed stakeholder approvals

- Security scan warnings

Triggers are documented for each risk in the Risk Register.

10. Risk Response Strategies

The following strategies are applied:

- Avoid: Change project approach to eliminate the risk.

- Mitigate: Reduce probability or impact through proactive action.

- Transfer: Shift risk to a third party where applicable.

- Accept: Acknowledge the risk and monitor it with no immediate action

11. Residual and Secondary Risks

- Residual risks are risks that remain after mitigation actions are applied.

- Secondary risks are new risks introduced by response strategies.

Both are documented and monitored.

12. Risk Monitoring and Reporting

Risk reviews are conducted:

- Bi-weekly during execution

- At the end of each increment

- Before UAT and deployment

Risk status is reported during:

- Schedule reviews

- Cost performance reviews

- Sponsor status meetings

13. Reserves and Risk Funding

- Contingency Reserve: 15% of estimated cost (70,500 EGP)

- Management Reserve: 20,000 EGP (Sponsor-controlled)

Use of reserves requires:

- Risk justification

- Sponsor approval

- Documentation in the Risk Register

13. Approval

Project Manager: Abdelrahman Alyan
Project Sponsor: Mr. Michael Bahgat
Supervisor: Eng. Abdelwahab Salah