Project Charter

Project Title:

University Financial Management System (FMS)

Project Start Date:

[Insert Date]

Projected Finish Date:

[Insert Date]

Project Managers:

Abdelrahman Alyan, Seif Wafikk , Youssef Nagui , Malak Montaser

Project Sponsor:

Mr.Michael – University Finance Department

1. Project Purpose / Justification

The purpose of this project is to design and develop a Financial Management System (FMS) that automates and centralizes the university’s financial operations.
This system will help improve efficiency, transparency, and accuracy in handling student payments, budgeting, expenditures, and reporting.

By eliminating manual financial processes, the university will reduce administrative errors, improve accountability, and gain better visibility over its financial health.

2. Project Objectives

- Automate student tuition fee payments and receipt generation.

- Provide tools for creating and managing departmental budgets.

- Track university-wide expenditures in real time.

- Generate detailed and accurate financial reports for management and auditing.

- Enhance data security, access control, and transparency.

3. High-Level Scope

The project covers the design, development, testing, and deployment of a web-based Financial Management System (FMS) with the following core modules:

- Student Payment & Fee Management

- Budget & Expenditure Management

- Reporting & Analytics Dashboard

- User Roles & Access Control

- Audit & Logging System

Out of Scope:

- Payroll management system for employees (future enhancement).

- Mobile app version (future phase).

4. High-Level Requirements

- Role-based authentication for different user types (students, staff, admin).

- Secure online payment gateway integration.

- Budget creation and approval workflows.

- Automated report generation in PDF and Excel formats.

- Audit trail for all transactions.

5. Major Deliverables

| Deliverable | Description |
| --- | --- |
| Project Charter | Defines purpose, objectives, and key stakeholders |
| Stakeholder Register | Identifies and categorizes all project stakeholders |
| Scope Statement | Defines the project’s boundaries and deliverables |
| Work Breakdown Structure (WBS) | Hierarchical decomposition of project work |
| Functional FMS Web Application | Developed and tested financial management system |
| User Documentation | User manual and admin guide for the FMS |
| Final Presentation | Project results and demonstration to stakeholders |

6. High-Level Risks

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Integration with existing systems may be complex | High | Early coordination with IT team |
| Data security vulnerabilities | High | Use encryption, secure login, and regular testing |
| Scope creep due to additional feature requests | Medium | Strict change control process |
| Limited user adoption or resistance to change | Medium | Conduct training and awareness sessions |
| Tight project deadlines | Medium | Use Agile sprints and proper time allocation |

7. Key Stakeholders

| Name | Role | Responsibility |
| --- | --- | --- |
| Finance Manager | Project Sponsor | Approve requirements, review progress |
| IT Department | Technical Support | Assist in integration and deployment |
| Students | End Users | Use the system for payments |
| Finance Staff | Primary Users | Manage budgets, expenses, and reports |
| Project Team | Developers & Testers | Build, test, and deliver the system |
| University Administration | Oversight | Evaluate and approve final system |

8. Milestones Schedule (Incremental Model)

| Increment | Description | Target Date | Responsible Party |
| --- | --- | --- | --- |
| Increment 1 | Project initiation & requirements gathering | Nov 10 – Nov 14, 2025 | PM Team |
| Increment 2 | Payment module (student fee management) | Nov 15 – Nov 24, 2025 | Web Team |
| Increment 3 | Budget & Expenditure module | Nov 25 – Dec 4, 2025 | Dev & Testing |
| Increment 4 | Reporting & Analytics Dashboard | Dec 5 – Dec 14, 2025. | Dev Team |
| Increment 5 | Audit & Access Control | Dec 15 – Dec 24, 2025. | Dev & Testing |
| Increment 6 | Integration, UAT, and Training | Dec 25, 2025 – Jan 10, 2026 | All Teams |

9. Estimated Project Cost

| Category | Description | Estimated Cost (EGP) |
| --- | --- | --- |
| Requirements & Design | Meetings, documentation, process modeling (e.g., with finance department) | 5,000 |
| Development Tools & Hosting | Domain (≈500 EGP/year), Hosting (≈3,000 EGP/year for VPS or cloud), SSL certificate, database costs | 3,500 |
| Development Labor | Team of 3–5 developers for ~3 months @ ~6,000 EGP/month each | 54,000 |
| Testing & QA | Test planning, automated test setup, bug fixing | 6,000 |
| Deployment & Integration | Server setup, CI/CD, connection with university finance database | 4,000 |
| Training & Documentation | Training sessions for finance department staff + user manual | 3,000 |
| Maintenance (1 Year) | Bug fixes, minor updates, cloud service renewal | 5,000 |
| Contingency (10%) | Buffer for unexpected costs (technical or resource delays) | 8,000 |
| Total Estimated Cost |  | ~88,500 EGP |

10. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Mr.Michael | Michael Bahgat | 11/04/2025 |
| Project Manager | Abdelrahman Alyan | __________________ | __________ |
| Dept. Supervisor | Eng.Abdelwahab Salah | __________________ | __________ |